## Tasks
Task | Task No | Tasks | Sub-tasks | Data required | Data source | Person responsible | Main WP | Other Relevant WP | External collaborator | Limitations | Modeling effort required
Species presence Identification | 1.1 | Maps of actual cetacean species presence | Cetacean in situ data collection (from aerial surveys, boat surveys) | Species presence | OBIS-TETHYS | Ward/Mithun | 2 |  | Giuseppe Notarbartolo diSciara | Some data might be need approval from TETHYS board of directors to be collected | no
|  |  |  | Species abundance | OBIS-TETHYS | Ward/Mithun | 5 |  | Simone Panigada |  | no
|  |  |  | Survey effort | OBIS-TETHYS | Ward/Mithun |  |  |  |  | no
|  |  | Cetacean sightings from Satellites | High resolution imagery (WorldView, other?) | Copernicus is too low resolution… | Palma | 4 |  | Peter Fretwell | High Cost of high resolution images
Archive data from DigitalGlobe
|  |  | Image classification to generate species occurrence maps based on satellite data | So far it is done by hand |  | Palma | 4 |  | (Peter's PhD student)
| 1.2 | Maps of potential cetacean species presence (here we will chose one of the two models) | Species feeding habitat modelling | Chlorophyll a | SeaWiFs | Guy | 6 | 4 | Jean-Noel Druon (JRC-EC) | Not really. Once we find a WP6 person to work on this Jean-Noel will work with them to adapt the model to our data/case | yes (Model developed by J-N Druon from JRC-EC for fin whales in the MED)- Druon et al 2012
MODIS Aqua Sensors
|  |  |  | Water Depth | GEBCO (www.bodc.ac.uk/products/ bodc_ products/gebco/)
|  |  |  | SST | MODIS Aqua; MODIS Terra
|  |  |  | Chlorophyll a fronts (proxy for food availability) | SeaWiFs
MODIS Aqua Sensors
|  |  | Species food web modelling | Chlorophyll a; NPP | SeaWiFs | Guy | 6 | 4 | Chiara Piroddi (Uni Barcelona) | The model at its current state doesn't discern species of the higher trophic level, thus needs to be adapted for fin whales and dolphins | Yes Ecopath with ECOSIM
MODIS Aqua Sensors
|  |  |  | Water Depth | GEBCO (www.bodc.ac.uk/products/ bodc_ products/gebco/)
|  |  |  | Sea Surface Salinity | MODIS Aqua; MODIS Terra
|  |  |  | Sea Bottom Salinity | ??
|  |  |  | Substratum | ??
|  |  |  | Trophic interactions | ??
|  |  |  | Fishing effort | ??
|  |  |  | Biological production of a species functional group (fishing mortality, predation mortality, net migration, biomass accumulation and other unexplained mortality) | ??
Data collection on drivers of population change | 2.1 | Maps of whale watching boat routes | Data collection on whale watching companies | Whale watching companies location |  | Amber | 7 |  |  |  | no
|  |  |  | Whale watching boat routes |  | Valia | 7 |  |  | 176 | no
| 2.2 | Maps of marine traffic | Shipping routes of large ships | Map of ship routes | Global Accessibility Map | Valia | 7 |  |  |  | no
| 2.3 | Cetaceans as fisheries bycatch |  | numbers of species dead as bycatch | http://www.ecoocean-institut.org/ | Johannes | 5 |  |  |  | no
| 2.4 | Maps of recreation boating and racing boats |  | number of racing boats | http://www.ecoocean-institut.org/recherche/impact-cet | Valia | 7 | 5 |  |  | no
|  |  |  | Port data on boats entering and leaving |  | Valia | 7 | 5 |  |  | no
|  |  |  | Port data on size of boats entering and leaving |  | Valia | 7 | 5 |  |  | no
| 2.5 | Underwater noise | Underwater noise modelling | Map of noise hotspots in the MED | Data and models available (still testing if we will include them) |  | 7 | 6 |  |  | yes (but we'll take available model outputs)
|  |  | Maps of impact of underwater noise on cetaceans |  |  |  | 7 | 6 |  |  | yes (but we'll take available model outputs)
Data collection on pecies value for tourism | 3.1 | Whale watching information | Database on number of whale watchers per season per year | Number of whale watching companies | ACCOBAMS | Amber | 7 | 5 |  |  | no
|  |  |  | Size of whale watching companies |  | Amber | 7 | 5 |  |  | no
|  |  |  | Number of tourists taking cruise for whale watching companies |  | Amber | 7 | 5 |  |  | no
|  |  |  | Whale watching company revenues |  | Amber | 7 | 5 |  |  | no
Ecosystem service mapping | 4.1 | Participatory mapping among stakeholders of whale watching benefits | Participatory map of whale presence |  | Collecting during the PPGIS workshop | Valia/Amber | 7 |  | Someone from 7.3 (Ana Stitih); Invited participants |  | mapping only
|  |  | Participatory map of threats to whale population |  |  | Valia/Amber
|  |  | Participatory map of whale watching spots |  |  | Valia/Amber
| 4.2 | Bayesian Belief Network for the Pelagos Sanctuary | Bayesian Belief Network for the Pelagos Sanctuary |  |  | Ana | 7.3
| 4.3 | Integrated modelling for ES related to whale watching tourism in the Pelagos Sanctuary | Maps of ES supply | Mapped outputs from tasks 1, 2 and 3 |  | Valia | 7 |  |  |  | YES (MIMES mostly)
|  |  | Maps of ES demand |  |  | Valia
| 5 | Communication of results with Pelagos Sanctuary | ES Survey |  |  | Francesca | 11
| 6 | Communication of results with general public | Design of short story |  |  | Alberto | 2